## Action Items
TASK | ASSIGNED TO | DUE DATE | COMPLETED Y/N | Additional Notes
Update the binders containing the lockout procedures for both buildings | Rachel/Shane | TBD |  | Cathy will be out again before RTK training
Create SDS Process | Rachel/Managers | TBD- Implementation of SMS JJ Keller |  | Waiting for SMS Implementation
Add extinguisher by the UV Web Press. Ground the Solvent Tote also | Dan/ Brian |  |  | Brian is looking into it
Repair lifts in 6905 | Dan | April Meeting
AWAIR Manual | Judy/Rachel | 2024-05-01 |  | Jusy emailed to the committee 4/18 to review
SDS Sheets - all complete, except for UV Press and Bldg B | Ricardo/Brian | April Meeting
Print Unsafe Conditions Forms and order 3 lock boxes for all faciltiies | Rachel | April Meeting | In progress | Need to order lock boxes, sheet has been updated
Update the Safety Process Posters on Bulletin Boards | Rachel | April Meeting
Schedule First Aid, CPR certification trainings | Rachel | 2024-05-01 |  | Send email looking for participation before scheduling
Weekly Safety Checklist | Managers | Ongoing |  | Check progress in May- LS and Finishing
Emergency Lighting- Replace | Rick | April Meeting |  | Ongoing- Ricardo and Rick working on it with electrician
Create the Quarterly Audit , share and discuss at Safety Meeting #3 in April | Rachel/Judy/Ricardo | 2024-05-01 |  | Received from Paul at PIM :)
Update Floor Plan Maps at all exits | Jackie/ Rachel | April Meeting |  | Still work in progress
Plan/ Schedule Fire Drill | Safety Committee | May |  | June- Emergency/Safety Awareness Week
Updating the New Hire Safety Orientation Checklist | Rachel | April Meeting |  | Sent new form to committee 4/18
169 door issue | Rob/ Property Management | Ongoing |  | Waiting for property management
Email Travelers about Benchmark of Injuries manufacturing | Rachel | 2024-05-01 |  | emailed Travelers 4/15/2024
Ask Travelers about Annual Audit Templates | Rachel | 2024-05-01 |  | emailed 4/15/2024
Look into creating a Smart Sheet for the 1st Report of Injury and Accident Investigation | TBD

## Completed
TASK | ASSIGNED TO | DUE DATE | COMPLETED Y/N | Additional Notes
Check the AED's to make sure those have not exceeded their expiration dates. | Dan/ Rob |  | YES
Contacts on the First Aid Kits | Rachel | 2023-12-11 | YES
Clear out the stair well bldg B | Rob + man power | 2024-02-01 | YES
OSHA 300 Form 2023 | Rachel | 2024-01-01 | YES
Secure the cords behind the machien in Mailing | Ricardo | 2024-02-15 | YES
Ensure the chocks are used at all of the parked trailers at bldg A | Rob | Ongoing | YES
Continue to document the monthly inspections of the material handling vehicles used in M | Rob | Ongoing | YES
Continue to document monthly inspections of the eye wash stations | TBD |  | YES
Switch Gear- Sign warning no one to operate other than Maintenance Dept | Rachel |  | Yes | Talk to Frank
Work Comp Injury Reduction Training- Travelers | Rachel |  | Received - Yes | emailed Maggie @ Travelers 2/23
Hoist Inspections | John Perry | Ongoing | Yes
Coordinate Right to Know Training | Rachel | 5/14, 5/15, 5/16 | Scheduled- Yes
Decibel reading/ PIM | Rachel | 2024-05-30 | Yes | Above 90 decibels- Report posted
Coordinate Audiometrics Training | Rachel | Scheduled |  | Scheduled in June
Tailgating Email | Rachel/Frank | 2024-03-20 | Sent | Ricardo and the managers have a process in place