## Action Items
TASK | ASSIGNED TO | DUE DATE | COMPLETED Y/N | Additional Notes
Ensure the chocks are used at all of the parked trailers at bldg A | Rob | Ongoing
Continue to document the monthly inspections of the material handling vehicles used in M | Rob | Ongoing
Update the binders containing the lockout procedures for both buildings | Rachel | TBD |  | emailed Cathy 2/23
Create SDS Process | Rachel | 2024-03-15
Hoist Inspections | John Perry | Ongoing
Add extinguisher by the UV Web Press. Ground the Solvent Tote also | Dan
Decibel reading/ PIM | Rachel | 2024-02-01 |  | emailed Cathy 2/23
Continue to document monthly inspections of the eye wash stations | TBD
Repair lifts in 6905 | Dan
AWAIR Manual | Judy/Rachel | 2024-03-31
SDS Sheets - all complete, except for UV Press and Bldg B | Ricardo
Print Unsafe Conditions Forms and order 3 lock boxes for all faciltiies | Rachel | 2024-03-15 | In progress | Need to order lock boxes, sheet has been updated
Update the Safety Process Posters on Bulletin Boards | Rachel | 2024-03-15
Schedule First Aid, CPR certification trainings | Rachel
Coordinate Right to Know Training | Rachel
Coordinate Audiometrics Training | Rachel
Monthly Safety Checklist
Requiring ALL production managers to participate in the Safety Program/Committee
Emergency Lighting- Repair | Rick | 2024-03-15 |  | emailed Rick 2/23
Switch Gear- Sign warning no one to operate other than Maintenance Dept | Rachel |  |  | Talk to Frank
Work Comp Injury Reduction Training- Travelers | Rachel |  |  | emailed Maggie @ Travelers 2/23

## Completed
TASK | ASSIGNED TO | DUE DATE | COMPLETED Y/N | Additional Notes
Check the AED's to make sure those have not exceeded their expiration dates. | Dan/ Rob |  | YES
Contacts on the First Aid Kits | Rachel | 2023-12-11 | YES
Clear out the stair well bldg B | Rob + man power | 2024-02-01 | YES
OSHA 300 Form 2023 | Rachel | 2024-01-01 | YES
Secure the cords behind the machien in Mailing | Ricardo | 2024-02-15 | YES