## Punchlist Q4 2024
TASK | ASSIGNED TO | DUE DATE | COMPLETED Y/N | Additional Notes
LOTO Process- work w/ Cathy M | Dan | 2025-03-01 | N
LOTO Training- work w/ Cathy
Safety Process and Emergency Contacts UPDATED on boards | Rachel | 2025-04-01 | N | Waiting for CPR and BBP Trainings to be completed
Bloodborne Pathogen/ First Aid CPR Training | Rachel | 2025-03-20 | N | March 2025- SCHEDULED
Eye Wash Station (A)- Sheet labeled w/ year. Remove eye wash station all together? | Rick/Rob | 2025-04-01 | N
Forklift Inspections (LS and Bldg B) | Beth/Rob | 2025-04-01 | N | LS= Tony, Bldg B= Mike (Temp)
PIT Recerts 2023/2024 | Rachel/ Maria | 2025-06-01 | N
Weekly Inspection, Change to MONTHLY Inspections | ALL Managers | Going forward | N
Tape the floor near the rollstand- Bldg A | Brian/Dan | 2025-04-01 | N
Paint Crosswalk under the skyway | Dan/Ed/Adam | 2025-04-01 | N
Lock Ladder in B (exterior ladder) | Dan/Ed/Adam | 2025-04-01
T250- Specific label (Fabric Softener) Digital | Brian | 2025-04-01
Open lids on containers | TBD
Train the Trainer- PIT Trainer | Rachel | 2025-06-01
Paperdust Cleaned up outside | Rick/Dan/Ed | 2025-04-01
Chock Postal Trailers (A) | Rob | 2025-04-01